# Agenda for MI Treehouse SEPA meeting

- Draft Schedule:  Overall anticipated timeline is approximately 6 months

  - Payment of initial deposit for EIS (50% of draft scope of work): $9,495.00 and payment of EIS fee: $2,832.50 (Total $12,327.50)

  - Start (Day 0)

  - Completion of contract with ESA for preparation of EIS (day 7)

  - Completion of DEIS (approximately day 67-97)

    - Submittal of additional information (TBD) by applicant by day 50

  - Notice of DEIS (approximately day 100)

  - Public comment on DEIS – 30 days (ends approximately day 130)

  - Review of public comment and preparation of FEIS (approximately day 160)

    - May require additional information (TBD) by applicant

  - Issuance of FEIS (approximately day 165)

- Review draft scope of work (attached)

- Other