## Comments
Section | Comment | Code Reference | Location in Submittal | Summary of Response
Geotech | From Michele Lorilla, City of Mercer Island Third-Party Geotechnical Peer Reviewer: “I reviewed the SUB3 package and my only outstanding comment is the same as before. The geotechnical engineer of record needs to provide a review letter of the planset and an updated statement of risk (SOR). The current package, although mentioning an updated SOR, provided the same one as before dated March 1, 2023” |  | NA | This will be provided as requested under separate cover.
Planning 1 | The public comment period for the shoreline variance permit applications ran from October 2, 2023 through November 3, 2023. Four comments were received. Please review and prepare responses to the public comments received during the public comment period (attached below). |  | Public Comment Responses spreadsheet | Response to public comment prepared. See spreadsheet with responses.
Planning 2 | It appears that the scope of the project has changed slightly from the last submittal on April 17, 2023. Please confirm that all of the information in the Critical Areas Study prepared by Anchor QEA, dated April 2023 accurately reflects the scope of the project |  | An updated Critical Areas Study is provided with this submittal. | The scope of the project had minor changes that are reflected in the Critical Areas Study, including details on project timing, coordination with Ecology regarding additional testing at the site, and mitigation sequencing approach - including the addition of a vegetation plan.
Planning 3 | There is a “DRAFT” stamp on the Wave and Wake Modeling Report prepared by Blue Coast Engineering, LLC, dated January 9, 2022 (Critical Areas Study Appendix E). Since this study is being used to demonstrate compliance with MICC 19.13.050(G) for the use of breakwaters, jetties, and weirs for protection of shoreline restoration areas, and for the variance criteria justifications, a finalized version of the report is required to be submitted |  | The final Wave and Wake Modeling Report is included as Critical Areas Study Appendix E. | The final Wave and Wake Modeling Report is included as Critical Areas Study Appendix E.
Planning 4 | SHL22-023 SSDP. The following comments were provided in the SUB1 review comments, on January 20, 2023. This information is required from the applicant to determine that the proposal complies with the standards in the SMP. These criteria will be used during review by the Hearing Examiner and Ecology to determine if the application is approvable, as discussed in the meeting held on June 26, 2023
4a | Provide separate mitigation sequencing specific to the breakwater per MICC 19.13.050(G). Mitigation sequencing is referenced several times in the application materials but does not specifically address this requirement | See tab for WAC 173-26-201(2)(e) | Mitigation sequencing for the central float structure is provided in the Cover Letter. | This requirement is specifically addressed for the central float.
4b | Provide more information on how the dock length or area for the public access pier is the minimum size necessary to meet the needs of the proposed water-dependent use for MICC 19.13.050(H)(3). The application states that the proposed dock is the minimum size necessary to meet the needs of programming at the site. Explain the needs of programming (ie expected attendance, peak hours, uses, etc | There is no dock length or area limit for public access piers, docks, or boardwalks; however, public access piers, docks, and boardwalks shall not interfere with navigation and shall be the minimum size necessary to meet the needs of the proposed water-dependent use | Cover letter table in response to MICC 19.13.050(H)(3) | Additional detail was provided describing how the dock length or area for the public access pier is the minimum size necessary to meet the needs of the proposed water-dependent use.
4c | Provide calculations for compliance with MICC 19.13.050(K)(4) for the increase in hardscape on the lot. If there is a net increase of more than 500 or 1000 square feet, a planting plan is required | See tab for MICC 19.13.050(K)(4) | See description in cover letter for how the project already satisfies the requirement. A vegetation plan is provided as Exhibit 9 for compliance. | The shoreline is already greater than 80% vegetated as surveyed by City staff and described in the vegetation plan in Exhibit 9. The vegetation plan is provided to comply with the intent of MICC 19.13.050(K)(4).
Planning 5 | Variances. The following comments were provided in the SUB2 review comment letter sent on June 26, 2023. More information is required from the applicant to determine that the proposal complies with the standards in the Washington Administrative Code (WAC). These criteria will be used during review by the Hearing Examiner and Ecology to determine if the application is approvable, as discussed in the meeting held on June 26, 2023
5a | Explanation of consistency with WAC 173-27-170 “The purpose of a variance permit is strictly limited to granting relief from specific bulk, dimensional or performance standards set forth in the applicable master program where there are extraordinary circumstances relating to the physical character or configuration of property such that the strict implementation of the master program will impose unnecessary hardships on the applicant or thwart the policies set forth in RCW 90.58.020” is missing from the consistency tables for all variances | See Tab on RCW 90.58.020 | See variance letters and compliance tables for additional information related to consistency with WAC 173-27-170. | Information from the application contents has been added to the compliance table demonstrating compliance with WAC 173-27-170 and RCW 90.58.020.
5b | Consistency with WAC 173-27-170(2)(e) – how is each variance the minimum necessary to afford relief from the hardship imposed by the strict application of the standards in the SMP? (ie. Why does the dock width need to be 10 ft versus 8 ft | See tab on WAC 173-27-170 | See variance letter and compliance tables for additional information related to consistency with WAC 173-27-170(2)(e). | Information from the application contents has been added to the compliance table demonstrating compliance with WAC 173-27-170(2)(e).
5c | Consistency with WAC 173-27-170(3)(a) – provide more detail on how the strict application of the standards in the SMP precludes reasonable use of the property | See tab on WAC 173-27-170 | See variance letters and compliance table for a definition of Reasonable Use and justification as requested. | The variance letters and compliance tables have been updated to demonstrate compliance with WAC 173-170(3)(a).
5d | SHL23-043 Dock Grating Variance Consistency with WAC 173-27-170(1) states that if the float were grated, light transmittance would be inhibited by structural components required to allow the wave attenuator/mooring float to provide critical safety functions for public use of the dock, including ADA accessibility and protection of shoreline ecological functions. This seems like creation of the hardship due to the design of the dock. The south floating dock is fully grated with an 8-foot width and larger piles. CPD may not be able to support this response in its staff report to the Hearing Examiner. Reconsideration of this response by the applicant is recommended | See tab on WAC 173-27-170 | Grating Variance 2 Exhibit 2, Pages 5, and Consistency Table | The variance letter and compliance table has been updated to provide additional details related to this request to more clearly demonstrate the need for this variance.
Planning 6 | SHL22-025 SCUP. The following comments were provided in the SUB1 review comments, on January 20, 2023. More information is required to determine if the proposal complies with the standards in the WAC. These criteria will be used during review by the Hearing Examiner and Ecology to determine if the application is approvable, as discussed in the meeting held on June 26, 2023
6a | Consistency with WAC 173-27-160(1)(a) – the applicant’s answer states that the proposed use of the Project will be consistent with RCW 90.58.020 by preserving the natural character of the shoreline. The application includes alteration of the shoreline by constructing hard shoreline stabilization measures, which does not preserve the natural character. CPD may not be able to support this response in its staff report to the Hearing Examiner. Reconsideration of this response by the applicant is recommended | See tab on WAC 173-27-160 | The cover letter compliance table consistency with WAC 173-27-160(1)(a). | The cover letter compliance table has been updated to provide additional details related to this request to more clearly demonstrate how the project and project elements preserve the natural character of the shoreline at this public park.

## WAC 173-26-201(2)(e)
(e) Environmental impact mitigation.
(i) To assure no net loss of shoreline ecological functions, master programs shall include provisions that require proposed individual uses and developments to analyze environmental impacts of the proposal and include measures to mitigate environmental impacts not otherwise avoided or mitigated by compliance with the master program and other applicable regulations. To the extent Washington's State Environmental Policy Act of 1971 (SEPA), chapter 43.21C RCW, is applicable, the analysis of such environmental impacts shall be conducted consistent with the rules implementing SEPA, which also address environmental impact mitigation in WAC 197-11-660 and define mitigation in WAC 197-11-768. Master programs shall indicate that, where required, mitigation measures shall be applied in the following sequence of steps listed in order of priority, with (e)(i)(A) of this subsection being top priority.
(A) Avoiding the impact altogether by not taking a certain action or parts of an action;
(B) Minimizing impacts by limiting the degree or magnitude of the action and its implementation by using appropriate technology or by taking affirmative steps to avoid or reduce impacts;
(C) Rectifying the impact by repairing, rehabilitating, or restoring the affected environment;
(D) Reducing or eliminating the impact over time by preservation and maintenance operations;
(E) Compensating for the impact by replacing, enhancing, or providing substitute resources or environments; and
(F) Monitoring the impact and the compensation projects and taking appropriate corrective measures.
(ii) In determining appropriate mitigation measures applicable to shoreline development, lower priority measures shall be applied only where higher priority measures are determined to be infeasible or inapplicable.
Consistent with WAC 173-26-186 (5) and (8), master programs shall also provide direction with regard to mitigation for the impact of the development so that:
(A) Application of the mitigation sequence achieves no net loss of ecological functions for each new development and does not result in required mitigation in excess of that necessary to assure that development will result in no net loss of shoreline ecological functions and not have a significant adverse impact on other shoreline functions fostered by the policy of the act.
(B) When compensatory measures are appropriate pursuant to the mitigation priority sequence above, preferential consideration shall be given to measures that replace the impacted functions directly and in the immediate vicinity of the impact. However, alternative compensatory mitigation within the watershed that addresses limiting factors or identified critical needs for shoreline resource conservation based on watershed or comprehensive resource management plans applicable to the area of impact may be authorized. Authorization of compensatory mitigation measures may require appropriate safeguards, terms or conditions as necessary to ensure no net loss of ecological functions.

## MICC 19.13.050(K)(4)
4
New development totaling 500 square feet or more of any combination of additional gross floor area, lot coverage or hardscape, including the primary structures and appurtenances, shall be required to provide native vegetation coverage over 50 percent of the 20-foot vegetation area shown on Figure C. This total shall include all gross floor area, lot coverage, and hardscape added in the five years immediately prior to the development proposal.
i.
New development totaling 1,000 square feet or more of any combination of additional gross floor area, lot coverage or hardscape, including the primary structures and appurtenances, shall be required to provide native vegetation coverage over 75 percent of the 20-foot vegetation area shown in Figure C.
ii.
A shoreline vegetation plan shall be submitted to the city for approval.
iii.
The vegetation coverage shall consist of a variety of ground cover shrubs and trees indigenous to the central Puget Sound lowland ecoregion and suitable to the specific site conditions. Existing mature trees and shrubs, but excluding noxious weeds, may be included in the coverage requirement if located in the 20-foot vegetation area shown in Figure C.
iv.
No plants on the current King County noxious weed lists shall be planted within the shorelands.

## RCW 90.58.020
Legislative findings—State policy enunciated—Use preference.
The legislature finds that the shorelines of the state are among the most valuable and fragile of its natural resources and that there is great concern throughout the state relating to their utilization, protection, restoration, and preservation. In addition it finds that ever increasing pressures of additional uses are being placed on the shorelines necessitating increased coordination in the management and development of the shorelines of the state. The legislature further finds that much of the shorelines of the state and the uplands adjacent thereto are in private ownership; that unrestricted construction on the privately owned or publicly owned shorelines of the state is not in the best public interest; and therefore, coordinated planning is necessary in order to protect the public interest associated with the shorelines of the state while, at the same time, recognizing and protecting private property rights consistent with the public interest. There is, therefore, a clear and urgent demand for a planned, rational, and concerted effort, jointly performed by federal, state, and local governments, to prevent the inherent harm in an uncoordinated and piecemeal development of the state's shorelines.
It is the policy of the state to provide for the management of the shorelines of the state by planning for and fostering all reasonable and appropriate uses. This policy is designed to insure the development of these shorelines in a manner which, while allowing for limited reduction of rights of the public in the navigable waters, will promote and enhance the public interest. This policy contemplates protecting against adverse effects to the public health, the land and its vegetation and wildlife, and the waters of the state and their aquatic life, while protecting generally public rights of navigation and corollary rights incidental thereto.
The legislature declares that the interest of all of the people shall be paramount in the management of shorelines of statewide significance. The department, in adopting guidelines for shorelines of statewide significance, and local government, in developing master programs for shorelines of statewide significance, shall give preference to uses in the following order of preference which:
(1) Recognize and protect the statewide interest over local interest;
(2) Preserve the natural character of the shoreline;
(3) Result in long term over short term benefit;
(4) Protect the resources and ecology of the shoreline;
(5) Increase public access to publicly owned areas of the shorelines;
(6) Increase recreational opportunities for the public in the shoreline;
(7) Provide for any other element as defined in RCW 90.58.100 deemed appropriate or necessary.
In the implementation of this policy the public's opportunity to enjoy the physical and aesthetic qualities of natural shorelines of the state shall be preserved to the greatest extent feasible consistent with the overall best interest of the state and the people generally. To this end uses shall be preferred which are consistent with control of pollution and prevention of damage to the natural environment, or are unique to or dependent upon use of the state's shoreline. Alterations of the natural condition of the shorelines of the state, in those limited instances when authorized, shall be given priority for single-family residences and their appurtenant structures, ports, shoreline recreational uses including but not limited to parks, marinas, piers, and other improvements facilitating public access to shorelines of the state, industrial and commercial developments which are particularly dependent on their location on or use of the shorelines of the state and other development that will provide an opportunity for substantial numbers of the people to enjoy the shorelines of the state. Alterations of the natural condition of the shorelines and shorelands of the state shall be recognized by the department. Shorelines and shorelands of the state shall be appropriately classified and these classifications shall be revised when circumstances warrant regardless of whether the change in circumstances occurs through man-made causes or natural causes. Any areas resulting from alterations of the natural condition of the shorelines and shorelands of the state no longer meeting the definition of "shorelines of the state" shall not be subject to the provisions of chapter 90.58 RCW.
Permitted uses in the shorelines of the state shall be designed and conducted in a manner to minimize, insofar as practical, any resultant damage to the ecology and environment of the shoreline area and any interference with the public's use of the water.

## WAC 173-27-170
The purpose of a variance permit is strictly limited to granting relief from specific bulk, dimensional or performance standards set forth in the applicable master program where there are extraordinary circumstances relating to the physical character or configuration of property such that the strict implementation of the master program will impose unnecessary hardships on the applicant or thwart the policies set forth in RCW 90.58.020.
(1) Variance permits should be granted in circumstances where denial of the permit would result in a thwarting of the policy enumerated in RCW 90.58.020. In all instances the applicant must demonstrate that extraordinary circumstances shall be shown and the public interest shall suffer no substantial detrimental effect.
(2) Variance permits for development and/or uses that will be located landward of the ordinary high water mark (OHWM), as defined in RCW 90.58.030 (2)(c), and/or landward of any wetland as defined in RCW 90.58.030 (2)(h), may be authorized provided the applicant can demonstrate all of the following:
(a) That the strict application of the bulk, dimensional or performance standards set forth in the applicable master program precludes, or significantly interferes with, reasonable use of the property;
(b) That the hardship described in (a) of this subsection is specifically related to the property, and is the result of unique conditions such as irregular lot shape, size, or natural features and the application of the master program, and not, for example, from deed restrictions or the applicant's own actions;
(c) That the design of the project is compatible with other authorized uses within the area and with uses planned for the area under the comprehensive plan and shoreline master program and will not cause adverse impacts to the shoreline environment;
(d) That the variance will not constitute a grant of special privilege not enjoyed by the other properties in the area;
(e) That the variance requested is the minimum necessary to afford relief; and
(f) That the public interest will suffer no substantial detrimental effect.
(3) Variance permits for development and/or uses that will be located waterward of the ordinary high water mark (OHWM), as defined in RCW 90.58.030 (2)(c), or within any wetland as defined in RCW 90.58.030 (2)(h), may be authorized provided the applicant can demonstrate all of the following:
(a) That the strict application of the bulk, dimensional or performance standards set forth in the applicable master program precludes all reasonable use of the property;
(b) That the proposal is consistent with the criteria established under subsection (2)(b) through (f) of this section; and
(c) That the public rights of navigation and use of the shorelines will not be adversely affected.

## WAC 173-27-160
Review criteria for conditional use permits.
The purpose of a conditional use permit is to provide a system within the master program which allows flexibility in the application of use regulations in a manner consistent with the policies of RCW 90.58.020. In authorizing a conditional use, special conditions may be attached to the permit by local government or the department to prevent undesirable effects of the proposed use and/or to assure consistency of the project with the act and the local master program.
(1) Uses which are classified or set forth in the applicable master program as conditional uses may be authorized provided that the applicant demonstrates all of the following:
(a) That the proposed use is consistent with the policies of RCW 90.58.020 and the master program;
(b) That the proposed use will not interfere with the normal public use of public shorelines;
(c) That the proposed use of the site and design of the project is compatible with other authorized uses within the area and with uses planned for the area under the comprehensive plan and shoreline master program;
(d) That the proposed use will cause no significant adverse effects to the shoreline environment in which it is to be located; and
(e) That the public interest suffers no substantial detrimental effect.
(2) In the granting of all conditional use permits, consideration shall be given to the cumulative impact of additional requests for like actions in the area. For example, if conditional use permits were granted for other developments in the area where similar circumstances exist, the total of the conditional uses shall also remain consistent with the policies of RCW 90.58.020 and shall not produce substantial adverse effects to the shoreline environment.
(3) Other uses which are not classified or set forth in the applicable master program may be authorized as conditional uses provided the applicant can demonstrate consistency with the requirements of this section and the requirements for conditional uses contained in the master program.
(4) Uses which are specifically prohibited by the master program may not be authorized pursuant to either subsection (1) or (2) of this section.